## Initial Plan
Color Coding |  | Completed |  |  |  | FALL 2022 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2022-09-13 | 2022-09-20 | 2022-09-27 | 2022-10-04 | 2022-10-11 | 2022-10-18 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-11-29 | 2022-12-06 | 2022-12-13 | 2022-12-20
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | ALL | 2022-09-14 | 2022-09-18 | 100%
| Confirm Project Team Roles | ALL | 2022-09-20 | 2022-09-21 | 100%
| Develop two business cases | ALL | 2022-09-11 | 2022-09-18 | 100%
| Develop Project Initiation Document (PID) | ALL | 2022-09-28 | 2022-10-09 | 100%
| Produce initial Project Plan, RACI | ALL | 2022-09-28 | 2022-10-09 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Murali | 2022-10-12 | 2022-10-16 | 100%
| Produce Context Diagram, Define System Interfaces | Navya | 2022-10-12 | 2022-10-16 | 100%
| Define Business Requirements | All | 2022-10-19 | 2022-10-23 | 100%
| Agree to System Requirements types | All | 2022-10-19 | 2022-10-23 | 100%
| Define Functional Decomposition | All | 2022-10-19 | 2022-10-23 | 100%
| Produce RCT document | Navya | 2022-10-19 | 2022-10-23 | 100%
| Decide which features to implement this semester | All | 2022-10-26 | 2022-10-30 | 100%
| Produce analysis diagrams (UML, DFD) | Asma | 2022-10-26 | 2022-10-30 | 100%
| Define functional requirements (User Stories) | Navya | 2022-10-26 | 2022-10-30 | 100%
| Complete Home Page Demo | Jigar,Lohith | 2022-10-26 | 2022-10-30 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Database Design (ERD) | Murali | 2022-11-09 | 2022-11-13 | 100%
| Database Specification | Tharun,Deva | 2022-11-09 | 2022-11-13 | 100%
| System Interface Design | Lohith | 2022-11-09 | 2022-11-13 | 100%
| User interface design | Lohith | 2022-11-09 | 2022-11-13 | 100%
| Architecture Diagram | Tharun,Murali | 2022-11-16 | 2022-11-20 | 100%
| Data Flow Diagram(Physical) | Venu,Asma | 2022-11-16 | 2022-11-20 | 100%
MILESTONE 3: DESIGN COMPLETED
Implementation & coding | Class Diagram (UML) | Navya | 2022-11-23 | 2022-11-27 | 100%
| Sequence Diagram (UML) | Deva | 2022-11-23 | 2022-11-27 | 100%
| Populate reference (static) data in database tables | Asma | 2022-11-23 | 2022-11-27 | 100%
| Feature Implementation - Create User Account - GUI | Jigar | 2022-11-23 | 2022-11-27 | 100%
| Feature Implementation - Create User Account - core | Jigar | 2022-11-23 | 2022-11-27 | 40%
| Feature Implementation - Log into Account - GUI | Jigar | 2022-11-23 | 2022-11-27 | 100%
| Feature Implementation - Log into Account - core | Jigar | 2022-11-23 | 2022-11-27 | 80%
| Feature Implementation - Search Restaurant - GUI | Jigar | 2022-11-23 | 2022-11-27 | 40%
| Feature Implementation - Create User Account - Field Validation | Jigar | 2022-11-23 | 2022-11-27 | 100%
| Database Design | Asma | 2022-11-23 | 2022-11-27 | 0%
| Testing | Asma | 2022-11-23 | 2022-12-04 | 100%
| validation | Asma | 2022-11-23 | 2022-11-27 | 0%
| Logging | Asma | 2022-11-23 | 2022-11-27 | 0%
| performance | Jigar | 2022-11-23 | 2022-11-27 | 0%
| GUI & Functionality Detailed Design | Jigar | 2022-10-26 | 2022-11-27 | 80%
| Establish code repository in GitHUb | Jigar | 2022-10-26 | 2022-10-30 | 100%
| Coding & Implemenation | Jigar | 2022-10-26 | 2022-11-27 | 80%
| Create Dev/QA Environments | Jigar | 2022-10-26 | 2022-10-30 | 30%
| Deployment | Jigar | 2022-10-26 | 2022-10-30 | 20%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | ALL | 2022-11-30 | 2022-12-04 | 100%
| Evaluate Features to be Tested | Jigar | 2022-11-30 | 2022-12-04 | 100%
| Design Test Cases | Navya | 2022-11-30 | 2022-12-04 | 100%
| User Story | Lohith | 2022-11-30 | 2022-12-04 | 100%
| Create User account - Core functionality | Asma | 2022-11-30 | 2022-12-04 | 100%
| Create User Account - GUI functionality | Asma | 2022-11-30 | 2022-12-04 | 100%
| Create User account - Field Validation - First Name | Asma | 2022-11-30 | 2022-12-04 | 100%
| Create User account - Field Validation - Last Name | Asma | 2022-11-30 | 2022-12-04 | 100%
| Create User account - Field Validation - Email | Asma | 2022-11-30 | 2022-12-04 | 100%
| Create User account - Field Validation - PhoneNumber | Asma | 2022-11-30 | 2022-12-04 | 100%
| Create User account - Field Validation - Password | Asma | 2022-11-30 | 2022-12-04 | 100%
| Create User account - Connectivity testing | Asma | 2022-11-30 | 2022-12-04 | 100%
| Create User account - Data Flow Out | Asma | 2022-11-30 | 2022-12-04 | 100%
| Log into Account - Core functionality | Jigar | 2022-11-30 | 2022-12-04 | 100%
| Log into Account - GUI functionality | Jigar | 2022-11-30 | 2022-12-04 | 100%
| Log into Account - Field Validation - Email | Jigar | 2022-11-30 | 2022-12-04 | 100%
| Log into Account - Field Validation - Password | Jigar | 2022-11-30 | 2022-12-04 | 100%
| Login to account - Connectivity testing | Jigar | 2022-11-30 | 2022-12-04 | 100%
| Login to account - Dataflow in | Jigar | 2022-11-30 | 2022-12-04 | 100%
| Login to account | Jigar | 2022-11-30 | 2022-12-04 | 100%
| Execute Test Cases | Asma | 2022-11-30 | 2022-12-04 | 100%
| Anaylze Test Results | ALL | 2022-11-30 | 2022-12-04 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2022-11-14 | 2022-12-20 | 0%