## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 02. Orders | 2.01 | Add items to cart | Search an API | 2023-03-24 | 2023-03-25 | 100% | Jigar Vaishnav
2 | 02. Orders | 2.01 | Add items to cart | Implement API | 2023-03-25 | 2023-03-26 | 100% | Jigar Vaishnav
3 | 02. Orders | 2.01 | Add items to cart | Create Add Button | 2023-03-27 | 2023-03-27 | 100% | Jigar Vaishnav
4 | 02. Orders | 2.01 | Add items to cart | Implement core functionality | 2023-03-27 | 2023-03-28 | 100% | Asma Batool
5 | 02. Orders | 2.01 | Add items to cart | Implement GUI requirments | 2023-03-27 | 2023-03-28 | 100% | Asma Batool
6 | 02. Orders | 2.01 | Add items to cart | Develop Test Cases for Add items to cart functionality | 2023-03-24 | 2023-03-28 | 100% | Lohith Kandakatla
7 | 02. Orders | 2.01 | Add items to cart | Test Add items to cart functionality | 2023-03-24 | 2023-03-30 | 100% | Tharun Donapati
8 | 04. User Account | 4.02 | Update User Account | Update API | 2023-03-24 | 2023-03-25 | 100% | Jigar Vaishnav
9 | 04. User Account | 4.02 | Update User Account | Implement API | 2023-03-25 | 2023-03-26 | 100% | Jigar Vaishnav
10 | 04. User Account | 4.02 | Update User Account | Display a form to Edit User Account Details | 2023-03-27 | 2023-03-27 | 100% | Jigar Vaishnav
11 | 04. User Account | 4.02 | Update User Account | Create an update and submit button | 2023-03-27 | 2023-03-28 | 100% | Jigar Vaishnav
12 | 04. User Account | 4.02 | Update User Account | Implement core functionality | 2023-03-27 | 2023-03-28 | 100% | Asma Batool
13 | 04. User Account | 4.02 | Update User Account | Implement GUI requirments | 2023-03-24 | 2023-03-28 | 100% | Asma Batool
14 | 04. User Account | 4.02 | Update User Account | Develop test Cases for Update User Account functionality | 2023-03-24 | 2023-03-30 | 100% | Lohith Kandakatla
15 | 04. User Account | 4.02 | Update User Account | Test Update User Account functionality | 2023-03-24 | 2023-03-30 | 100% | Tharun Donapati

## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 01. Search | 1.01 | Search Restaurant | Search an API | 2023-02-20 | 2023-02-21 | 100% | Jigar Vaishnav
2 | 01. Search | 1.01 | Search Restaurant | Implement API | 2023-02-21 | 2023-02-23 | 100% | Jigar Vaishnav
3 | 01. Search | 1.01 | Search Restaurant | Implement core functionality | 2023-02-23 | 2023-02-25 | 100% | Asma Batool
4 | 01. Search | 1.01 | Search Restaurant | Implement GUI requirments | 2023-02-23 | 2023-02-27 | 100% | Asma Batool
5 | 01. Search | 1.01 | Search Restaurant | Develop Test Cases for search restaurant functionality | 2023-02-27 | 2023-02-28 | 100% | Lohith Kandakatla
6 | 01. Search | 1.01 | Search Restaurant | Test search restaraunt functionality | 2023-03-01 | 2023-03-02 | 100% | Tharun Donapati
10 | 01. Search | 1.02 | Search Recipes | Search an API | 2023-02-20 | 2023-02-21 | 100% | Jigar Vaishnav
11 | 01. Search | 1.02 | Search Recipes | Implement API | 2023-02-21 | 2023-02-23 | 100% | Jigar Vaishnav
11 | 01. Search | 1.02 | Search Recipes | Implement core functionality | 2023-02-23 | 2023-02-25 | 100% | Asma Batool
12 | 01. Search | 1.02 | Search Recipes | Implement GUI requirments | 2023-02-23 | 2023-02-27 | 100% | Asma Batool
12 | 01. Search | 1.02 | Search Recipes | Develop test Cases for search receipe functionality | 2023-02-27 | 2023-02-28 | 100% | Lohith Kandakatla
13 | 01. Search | 1.02 | Search Recipes | Test search receipe functionality | 2023-03-01 | 2023-03-02 | 100% | Tharun Donapati