## Road Map
FOOD EXPRESS
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 3/03/2023 | Iteration 2 - 3/31/2023 | Iteration 3 - 4/21/2023 | Iteration 4 - 5/12/2023
01. Search | 01.01 Search for Restaurants | 4 | X
| 01.02 Search Recipes | 4 | X
| 01.03 Search Beverages | 2
02. Orders | 02.01 Add items to cart | 4 |  | X
| 02.02 Order Placement | 4 |  |  | X
| 02.03 Accept/Reject orders | 3
| 02.04 Update Order Status | 3
03. Payments | 03.01 Add Payment Details | 4 |  |  | X
| 03.02 Update Payment Details | 4 |  |  |  | X
| 03.03 Make Payment | 3
04. User Account | 04.01 Create User Account | 2
| 04.02 Update User Account | 4 |  | X
| 04.03 Cancel User Account | 4
| 04.04 Log into Account | 7
| 04.05 Opt Subscription Plan | 2
| 04.06 Cancle Subscription Plan | 2
| 04.07 Renew Subscription Plan | 2
| 04.08 Contact Customer support | 2
| 04.09 Add rating/review | 4 |  |  |  | X
| 04.10 Add Restaurant Details | 1
| 04.10 Update Restaurant Details | 2
05. Advertisement | 05.01 Create Ad | 2
| 05.02 Update Ad | 2
| 05.03 Delete Ad | 2
| 05.04 Expire Ad | 2
|  | VELOCITY: | 8 | 8 | 8 | 8

## Story Map
Epics |  | FOOD EXPRESS - User Story Map
Epic 1 - Search |  | Epic 1 - Search | Epic 2 - Orders | Epic 3 - Payments | Epic 4 - User Account | Epic 5 - Advertisement
Epic 2 - Orders | User Stories | 01.01 Search for Restaurants
Epic 3 - Payments |  | 01.02 Search Recipes |  |  |  |  | Iteration 1
Epic 4 - User Account |  |  | 02.01 Add items to cart
Epic 5 - Advertisement |  |  |  |  | 04.02 Update User Account |  | Iteration 2
02.02 Order Placement
|  |  |  | 03.01 Add Payment Details |  |  | Iteration 3
|  |  |  | 03.02 Update Payment Details | 04.09 Add rating/review |  | Iteration 4