## I4
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 03. Payments | 3.02 | Update Payment Details | Update API | 2023-04-22 | 2023-04-26 | 100% | Jigar Vaishnav
2 | 03. Payments | 3.02 | Update Payment Details | Implement API | 2023-04-22 | 2023-04-26 | 100% | Jigar Vaishnav
3 | 03. Payments | 3.02 | Update Payment Details | Display a form to Update payment Details | 2023-04-26 | 2023-04-28 | 100% | Jigar Vaishnav
4 | 03. Payments | 3.02 | Update Payment Details | Create an Update payment Details button | 2023-04-26 | 2023-04-28 | 100% | Jigar Vaishnav
5 | 03. Payments | 3.02 | Update Payment Details | Implement core functionality | 2023-04-26 | 2023-04-28 | 100% | Asma Batool
6 | 03. Payments | 3.02 | Update Payment Details | Implement GUI requirments | 2023-04-26 | 2023-04-28 | 100% | Asma Batool
7 | 03. Payments | 3.02 | Update Payment Details | Develop test Cases for Update Payment details functionality | 2023-04-29 | 2023-05-04 | 100% | Lohith Kandakatla
8 | 03. Payments | 3.02 | Update Payment Details | Test Update Payment Details functionality | 2023-04-29 | 2023-05-04 | 100% | Tharun Donapati
9 | 04. User Account | 4.09 | Add rating/review | Implement API | 2023-04-22 | 2023-04-26 | 100% | Jigar Vaishnav
10 | 04. User Account | 4.09 | Add rating/review | Display a form to Add rating/review | 2023-04-26 | 2023-04-28 | 100% | Jigar Vaishnav
11 | 04. User Account | 4.09 | Add rating/review | Create a button to Add rating/review | 2023-04-26 | 2023-04-28 | 100% | Jigar Vaishnav
12 | 04. User Account | 4.09 | Add rating/review | Implement core functionality | 2023-04-26 | 2023-04-28 | 100% | Asma Batool
13 | 04. User Account | 4.09 | Add rating/review | Implement GUI requirments | 2023-04-26 | 2023-04-28 | 100% | Asma Batool
14 | 04. User Account | 4.09 | Add rating/review | Develop Test Cases for Add rating/review functionality | 2023-04-29 | 2023-05-04 | 100% | Lohith Kandakatla
15 | 04. User Account | 4.09 | Add rating/review | Test Add rating/review functionality | 2023-04-29 | 2023-05-04 | 100% | Tharun Donapati

## I3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 02. Orders | 2.02 | Order placement | Update API | 2023-04-01 | 2023-04-08 | 100% | Jigar Vaishnav
2 | 02. Orders | 2.02 | Order placement | Implement API | 2023-04-09 | 2023-04-14 | 100% | Jigar Vaishnav
3 | 02. Orders | 2.02 | Order placement | Create place order Button | 2023-04-15 | 2023-04-16 | 100% | Jigar Vaishnav
4 | 02. Orders | 2.02 | Order placement | Implement core functionality | 2023-04-16 | 2023-04-18 | 100% | Asma Batool
5 | 02. Orders | 2.02 | Order placement | Implement GUI requirments | 2023-04-16 | 2023-04-18 | 100% | Asma Batool
6 | 02. Orders | 2.02 | Order placement | Develop Test Cases for Order placement functionality | 2023-04-16 | 2023-04-20 | 100% | Lohith Kandakatla
7 | 02. Orders | 2.02 | Order placement | Test Order placement functionality | 2023-04-16 | 2023-04-20 | 100% | Tharun Donapati
8 | 03. Payments | 3.01 | Add Payment Details | Update API | 2023-04-01 | 2023-04-08 | 100% | Jigar Vaishnav
9 | 03. Payments | 3.01 | Add Payment Details | Implement API | 2023-04-09 | 2023-04-14 | 100% | Jigar Vaishnav
10 | 03. Payments | 3.01 | Add Payment Details | Display a form to Add payment Details | 2023-04-15 | 2023-04-16 | 100% | Jigar Vaishnav
11 | 03. Payments | 3.01 | Add Payment Details | Create an Add payment Details button | 2023-04-16 | 2023-04-18 | 100% | Jigar Vaishnav
12 | 03. Payments | 3.01 | Add Payment Details | Implement core functionality | 2023-04-16 | 2023-04-18 | 100% | Asma Batool
13 | 03. Payments | 3.01 | Add Payment Details | Implement GUI requirments | 2023-04-16 | 2023-04-28 | 100% | Asma Batool
14 | 03. Payments | 3.01 | Add Payment Details | Develop test Cases for Add Payment functionality | 2023-04-16 | 2023-04-20 | 100% | Lohith Kandakatla
15 | 03. Payments | 3.01 | Add Payment Details | Test Add Payment Details functionality | 2023-04-16 | 2023-04-20 | 100% | Tharun Donapati